## Slide 1: Estimating effort and cost
Calum Arthur, Liam Bell, Euan Boyle

## Slide 2: How can we estimate the effort and cost that a project will involve?
What is an estimate?
Estimating successfully provides the client with;
  The tasks that will be done
  The resources involved
  The rate of the cost of work and
  The duration of the project, in days, weeks or months, possibly in years.
Two of the ways that we can estimate effort;
  Fixed price work packages
  Early termination

## Slide 3: Why is it estimating effort and cost important?
Project budgets are usually the deciding factor on a project
Estimating provides a price
Estimating provides clarity
Estimating provide milestones

## Slide 4: Why is it difficult?
Getting the balance right
High stress/pressure
No two projects are the same
Problems in development

## Slide 5: COCOMO
Constructive Cost Model
Est. in late 70s
  Published in Boehm’s book Software Engineering Economics in 1981
Based on the Waterfall Model
  However, COCOMO only provides effort estimates for the development phases only:
    Design
    Implementation
    Integration
    Testing
    Requirements
    Maintenance
Notes: Requirements and Maintenance phases are estimated as separate quantities

## Slide 6: What is it?
Provides formulas for estimating total development effort and time
Effort depends on amount of software to be produced
  Measured in DSI
Effort is adjusted to account for effects of cost drivers

## Slide 7: COCOMO Development
Three levels of detail of COCOMO:
  Basic
  Intermediate
  Detailed
Three development modes:
  Organic (PM = 2.4 (KDSI)1.05
  Semi-detached (PM = 3.0 (KDSI)1.12
  Embedded (PM = 3.6(KDSI)1.20

## Slide 8: Advantages and Disadvantages
Highly detailed
Based on empirically derived equations (factual)
Accounts for many variables in project
Works on historical data
Ignores requirements and documentation
Requires prediction of project size
Ignores customer skills

## Slide 9: Function Point Method
The concept of Function Points was introduced by Alan Albrecht of IBM in 1979 and later revised in 1984.
Objectives
Measure software by quantifying the functionality requested by and provided to the customer.
Measure software development and maintenance independently of technology used for implementation.
Measure software development and maintenance consistently across all projects and organizations.

## Slide 10: What is a Function Point?
A Standard Unit of Measure that represent the functional size of a software application.
Measured from the user’s perspective.
An ISO Standard.

## Slide 11: Pros Cons
Technology-independent
FP data repositories
Low Cost
Used to estimate effort for projects
Requires a lot of knowledge about the effort of similar projects
Subjective judgement is involved

## Slide 12: Five Step Counting Process
Determine the type of count.
  Development Project FP Count
  Enhancement Project FP Count
  Application FP Count
Identify the scope and boundary of the count.
Determine the unadjusted FP count.
Determine the Value Adjustment Factor.
Calculate the Adjusted FP Count.

## Slide 13: Determining the unadjusted FP count
Data Functions - Internal Logical Files (ILFs)
Data Functions - External Interface Files (EIFs)
Transaction Functions - External Inputs (EI’s)
Transaction Functions - External Outputs (EO’s)
Transaction Functions - External Inquiries (EQ's)

## Slide 14: Determining the Value Adjustment Factor
The Value Adjustment Factor (VAF) consists of 14 General System Characteristics
Data Communication
Distributed data processing
Performance
Heavily used configuration
Transaction rate
Online data entry
End user efficiency
Online update
Complex processing
Reusability
Installation ease
Operational ease
Multiple sites
Facilitate change
VAF = (TDI*0.01) + 0.65
0 - Not present, or no influence
1 - Incidental influence
2 - Moderate influence
3 - Average influence
4 - Significant influence
5 - Strong influence throughout

## Slide 15: Calculate the Adjusted Function Point Count
Adjusted FP Count = Unadjusted FP Count * VAF

## Slide 16: Relating to Case Study…
Type of Count: Enhancement Project FP Count
Scope: Implementing Extension
Boundary: Outputs; Screens, Other forms of output.
Determine FP count
Determine Value Adjustment Factor
Calculate the Adjusted FP Count