## Slide 1: Managing Risk
Software project management

## Slide 2: A broad understanding:
We all have an inherent understanding of a what a risk is and the natural ability to assess risks which we encounter in life:
Notes: People and animals alike have an inherent understanding of risk. It came from a need to protect our lives and survive in the world but naturally as society has developed the need to understand new non-biological risks has developed.

## Slide 3: Risk Management in the workplace:
Procedural
Management
Training
Seminar
Even careers!
  “…Risk management involves understanding, analysing and addressing risk to make sure organisations achieve their objectives.”
- Institute of Risk Management

## Slide 4: What is risk management about?
Risk management is about taking practical steps to protect people from real harm and suffering - not bureaucratic back covering. Taking a sensible approach to risk management is about:
  ensuring that workers and the public are properly protected
  enabling innovation and learning, not stifling them
  ensuring that those who create risks manage them responsibly and understand that failure to manage significant risks responsibly is likely to lead to robust action
  providing overall benefit to society by balancing benefits and risks, with a focus on reducing significant risks - both those which arise more often and those with serious consequences
  enabling individuals to understand that as well as the right to protection, they also have to exercise responsibility
HSE - hse.gov.uk

## Slide 5: How does this relate to software project management?

## Slide 6: Risk management in software project management
Assessment
  Identify risks and their triggers
  Analyse/Classify
  Prioritize all risks
Control
  Craft a plan that links each risk to a mitigation
  Monitor for risk triggers during the project
  Implement the mitigating action if any risk materializes
  Communicate risk status throughout project
Castsoftware.com
Boehm’s Risk-Management Process (Dr. E. Wallmüller)

## Slide 7: The RMMM PLAN
As risk management is a project in itself it is often useful to implement a Risk Mitigation, Monitoring and Management plan.
An RMMM plan is a dynamic document detailing the assessment and control phases of risk management.
As the project progresses the RMMM can be updated to reflect any changes to previously identified risks or add any newly identified risks.
For every risk identified a description is given along with its probability and impact, mitigation, monitoring and management
Responsibility of the project manager.

## Slide 8: The RMMM PLAN outline
1.0 Introduction
This section provides an overview of the RMMM Plan.
1.1 Scope and intent of RMMM activities
A description of the overall RMMM focus including objectives, organizational responsibilities.
1.2 Risk management organizational role
Description of who has responsibility for risk management.
2.0 Project risks
This section describes all known project risks.
2.1 Risk table
A presentation of all risks, probabilities and impact.
2.1.1 Description of risk m
Risk m is described along with relevant subconditions. Section2.1.1 is repeated for each of m risks.
2.1.2 Probability and impact for risk m
Probability and impact for risk m is described Section 2.1.2 is repeated for each of m risks.
2.2 Risk refinement
High probability/high impact risks are refined using the CTC approach.

## Slide 9: The RMMM PLAN outline continued
3.0 Risk mitigation, monitoring, and management
This section discusses RMMM for each risk.
3.1 Risk mitigation for risk m
How do we avoid risk m? Section 3.1 is repeated for each of m risks.
3.2 Risk monitoring for risk m
What conditions do we monitor to determine whether risk m is becoming more or less likely? Section3.2 is repeated for each of m risks.
3.3 Risk management for risk m
What contingency plans should we put into plan under the assumption that risk m will occur? Section 3.3 is repeated for each of m risks.
4.0 Special conditions
A discussion of special conditions that may trigger project critical risks and the actions required s hould these conditions occur.

## Slide 10: Software project management: what are the risks?
https://www.brighthubpm.com/risk-management/47932-risks-involved-in-software-project-management/
Categories of Risks in Software Projects
Schedule Risks
Budget Risks
Operational Risks
Technical Risks
Other Unavoidable Risk
Notes: Schedule / Time-Related / Delivery Related Planning Risks
These risks are related to running behind schedule and are essential time-related risks, which directly impact the delivery of the project.
Some of the reasons for such risks are
Incorrect Time Estimation, and consequently an incorrect project schedule
Improper Resource Allocation
Underutilization of Resources
Superficial Understanding of Project Complexities
Unexpected Expansion of Project Scope
Incorrect time estimation may occur because activities may have external dependancies such as client approvals, subcontractors etc. and a delay in a critical path activity has a cascading effect on the entire project.
Resource Allocation may be improper / Underutilization of resources may take place, especially if resources are shared between projects.
A silo approach of members in various teams in a project may lead to an isolated superficial understanding of project complexities which may result in delays in subsequent stages e.g. when different development teams work on various aspects of a software project and run into issues during system/integration testing.
Budget / Financial Risks
These are the monetary risks which are associated with budget overruns.
Some of the reasons for such risks are
Improper Budget Estimation
Cost Overruns due to underutilization of resources
Expansion of Project Scope
Improper Tracking of Finances
Underutilization of resources especially happens when resources are shared between projects because it becomes difficult to effectively manage such resources and a certain amount of productivity may go waste.
Further, unexpected expansion of project scope (due to addition of features by clients, etc) may lead to budget overruns as such expansions may not have been factored in to the original estimates.
Delay of projects may also have certain penalty costs associated with it e.g. construction projects
Operational / Procedural Risks
These are risks which are associated with the day-to-day operational activities of the project.
These could be due to any of the below reasons
Improper Process Implementation
Silo approach followed by software development teams leading to conflicts
Conflicting Priorities
Lack of conflict resolution / team spirit
Lack of clarity in responsibilities
Breakdown in communications
Lack of sufficient training
Effective team communication is an essential part of project management and in people-intensive projects such as software projects, there is a strong need for an established communication structure, a setup for escalation, a conflict resolution process, established project priorities and above all, the employees need to be trained in making use of these processes within the organization.
Technical / Functional / Performance Risks
These are technical risks associated with the functionality of the software or with respect to the software performance.
In order to compensate for excessive budget overruns and schedule overruns, companies sometimes reduce the functionality of the software.
Software testing is a downstream stage in the software development lifecycle and as the project falls behind schedule, downstream activity times are shrunk in order to meet delivery dates which results in insufficient software testing.
Further, developers face a constant trade-off between achieving maximum functionality of the software (in terms of software features) and peak performance (maximum speed and quick response time by minimizing and eliminating unnecessary frills from the software)
In order to maintain the sanctity of the software development process, while simulatenously catering to the customers needs, a mutually agreed-upon cut-off date should be determined, beyond which "expected software functionality" would be frozen and any further requirements would be handled in subsequent softwares releases.
Other Unavoidable Risks
All the risks described above are those which can be anticipated to a certain extened and planned for in advance. However there are certain risks which are unavoidable in nature.
The reasons for such unavoidable risks are described below.
Changes in government policy
Obsolescence of software due to new technology from a rival company
Loss of contracts due to changes at customers end
Although these risks are broadly unavoidable, an organization may anticipate and thereby reduce the impact of such risks by
keeping abreast with changes in government policy
monitoring the competition
catering to the needs of the customer and ensuring customer satisfaction

## Slide 11: CASE STUDy 1: Bournemouth College
About the project:
Used to be managed by local government, now autonomous
Payroll administered by local authority, who now charges for the service
Is an off the shelf payroll package cheaper?
Categories of Risks in Software Projects
Schedule Risks
Budget Risks
Operational Risks
Technical Risks
Other Unavoidable Risks
Risks?
Finishing the previous contract before the software is ready
Contract may have financial/time constraints
Cost of payroll package
May need multiple employees for the department
Local government may say no
No suitable off the shelf package

## Slide 12: CASE STUDy 1: Bournemouth College
About the project:
Used to be managed by local government, now autonomous
Payroll administered by local authority, who charges for the service
Is an off the shelf payroll package cheaper?
Draft RMMM plan:
1.0 Introduction
Responsible: Information Systems Development Officer
2.0 Risks (see slide before for examples)
3.0 Risk Mitagation, Monitoring and Management
e.g.
Risk: May need multiple employees for the new department
Monitoring: Assess word load and work load projections for finished
project
Management: Plan for hiring, budget, office space etc.
4.0 Special Conditions
e.g. local government says no to deal

## Slide 13: Thank you!
Any questions?