## Slide 1
Risk Management

## Slide 2
Categories of risk
01
Framework for dealing with risk
02
Risk identification
03
Risk assessment
04
Risk planning
05
Risk management
06
Evaluating risk to the seclude
07
PERT
08
Monte Carlo simulation Critical chain concepts
09

## Slide 3: What is a risk?

## Slide 4: PM-BOK
Project
Management
Body
Of
Knowledge
PM-BOK is a project management standard published by the Project Management Institute in the USA
“an Uncertain event or condition that occurs, has a positive or a negative effect on a projects objectives.”

## Slide 5: PRINCE2
PRojects
IN
Controlled
Environments
PRINCE2 is the UK government sponsored Project Management standard
“The chance of exposure to the adverse consequences of future events.”

## Slide 6: Category of risks
Actors– People involved in development
Technology- Technology used to implement the application
Structure- Management structure and systems
Tasks- The work planned
Risks often arise form relationships between factors.

## Slide 7: Planning for risk
1
2
3
4
Risk Identification
Risk analysis and prioritization
Risk planning
Risk monitoring

## Slide 8: Risk identification
Checklist
Brainstorming
TOOLS:
&

## Slide 9: Risk analysis and prioritization
Within the project there may be an endless amount of risks. We can distinguish the likely risks and their damage by estimating the Risk Exposure with this formula:
Risk Exposure =
(potential damage) x (probability of occurrence)

## Slide 10: Risk Planning
Risk Acceptance
Risk Reduction
Risk Migration
Risk Transfer

## Slide 11: Risk monitoring
When you decided which risks appear to be the most harmful to your project, you will then be expected to produce a Risk Assessment or Risk Register.
Risk description
Risk Impact
Risk migration plan
Probability of impact
Costs

## Slide 12
Risk ID
Owner
Risk Title
Date raised
Risk Description
Impact Description
Recommended Risk Migration
Probability/Impact Values
Pre-migration
Post-migration
Probability
Cost
Duration
Quality

## Slide 13: Case Study 1: Payroll Processing at Brightmouth College
Risks involved with “Off-the-shelf” software:
Time delay in installation
Software may be complex
Bugs
Adjustments may need to be implemented
Data transfer and conversion issues

## Slide 14: Contingency
What is it?
  Planned action to be carried out if a particular risk occurs
What is a contingency plan?
  The steps you would take if the risk occurs
Always be prepared
May need to pay for a contingency plan

## Slide 15: Is it worth it?
Risk Reduction Leverage (RRL)
  Is this risk reduction cost effective?
RRL = (REB - REA) / Cost of risk reduction
REB: Risk Exposure before risk reduction has be taken
REA: Risk Exposure after risk reduction has be taken
RRL > 1.0, The reduction of risk is greater than the cost

## Slide 16: How to keep track of risks
Risk Register
  A record of the most threatening risks to a project
Expect the size to change
  Find new risk -> add to register
  Risks no longer relevant -> remove from register

## Slide 17
Risk ID
Owner
Risk Title
Date raised
Risk Description
Impact Description
Recommended Risk Migration
Probability/Impact Values
Pre-migration
Post-migration
Probability
Cost
Duration
0000
Instillation delay
Herbert
14/1/2019
Delay in integrating payroll software for staff
Staff without pay
Install in the beginning of working the year. Less data to be transferred.
70%
£2500
14 Days
Case Study 1

## Slide 18: Scheduling with risks
If your initial time estimations don’t include risk
  Be ready to compensate
How to include risk?
  PERT
    Take uncertainty into account
  Monte Carlo Simulation
    Take uncertainty into account (but better)

## Slide 19: PERT
Program Evaluation & Review Technique
Similar to the Critical Path Method (CMP)
Has 3 estimations for duration of a task
  Most likely time: m, time we expect to complete a task
  Optimistic time: a, the shortest time possible
  Pessimistic time: b, the longest time possible
Te: Expected duration for the task
Te = (a + 4m + b)/ 6

## Slide 20: PERT
PERT node
The corners are dates
Duration: How long we calculated
Float: How long we can take a break
Nodes have many variations

## Slide 21: PERT Example

## Slide 22: Monte Carlo Simulation
Much more realistic way of describing uncertainty
Building models using a probability distribution
  How long has it taken to complete a similar task before
  What are the most common time ranges
Frequency Histogram
Cumulative Probability Plots
Software is your friend

## Slide 23: Critical Chain Concept
Resource focused
Steps
  Estimate Time
  Cut time in half Add to time to buffer
Track the buffer time

## Slide 24: Case Study 1: Payroll Processing at Brightmouth College
Information Systems Development Officer, plan the project
  Finding the risks
    Creating risk register
  Scheduling the appropriate dates
    PERT
    Monte Carlo
    Critical Chain Concepts
Prove the worth of the “off-the-shelf”
  RRL
If it’s not they should have a contingency plan
  Finding different software
  Evaluate their spending

## Slide 25: References
Hughes and Cotterell, Software Project Management, 4th / 5th edition, Chapter 7
https://www.arrkgroup.com/thought-leadership/bespoke-or-off-the-shelf-software-a-comparison/
https://toughnickel.com/business/PERT-Chart-for-PM
https://www.management-hub.com/project-management-tools-pert-gantt-run-chart.html
https://www.palisade.com/risk/monte_carlo_simulation.asp